后院改造施工规划

8958 Fraser River Street, Littleton, CO

Lot 137 · Sterling Ranch Filing No. 4A · Douglas County

海拔 5,721 ft · 地块面积 6,448 sq ft

# 一、项目概览

本规划基于地块平面图（Plot Plan，Aztec Consultants，2021年5月18日）及实地照片，覆盖后院全面改造施工内容。改造目标为将现有低利用率后院升级为功能完善的户外生活空间，降低草坪维护负担，保留儿童和宠物活动区域。

## 地块关键数据

| 项目 | 数值 | 备注 |
| --- | --- | --- |
| 后院宽度（南北） | 66.19 ft | 东侧围栏 |
| 后院纵深（东西） | ~45 ft | 房屋后墙到东围栏 |
| 北侧余量 | 18.1 ft | 房屋北墙到北围栏 |
| 南侧余量（Pathway） | 9.96 ft | 现有水泥路 |
| Deck / Patio | 20 × 10 ft | 在房屋矩形内 |
| 楼梯 | 20 ft × ~4 ft | 悬挂在东墙外 |
| 后院退线 | 15 ft | Douglas County要求 |
| 草坪主坡度 | 7.9% | 向东下坡 |
| 南侧Pathway坡度 | 13% | 现有水泥，保留 |
| 北侧区域坡度 | 10% | 扩展Patio区域 |

## 改造范围总览

| 功能区 | 现状 | 改造内容 | 方式 |
| --- | --- | --- | --- |
| 北侧扩展Patio | 碎石+草地 | 新建石板/混凝土铺装，dining+烧烤区，座椅矮墙 | DIY/半DIY |
| 东扩通道 | 草地 | 楼梯东侧4ft宽石板通道，弧形切角连接北扩Patio | DIY |
| 东扩南部水泥条 | 草地 | 4ft宽延伸至South Pathway，形成连通路径 | DIY |
| 现有Patio整修 | 混凝土（杂物） | 清理整修，作为核心活动区 | DIY |
| Fire Pit区 | 草地/碎石 | 局部找平，放置可移动fire pit | DIY |
| 草坪改造 | 贫瘠，易长杂草 | 缩小至~870 sqft保留区，补种耐旱草种 | DIY |
| Mulch种植区 | 碎石 | weed barrier+mulch+脚踏石板 | DIY |
| 东侧隔离带 | 碎石+黑色mulch（现有） | 保留现状 | 无需施工 |
| Garden Box (×3) | 现有3个 | 保留，周边整理mulch通道 | DIY微调 |
| 灌溉系统 | 2管8喷头 | 重新布线，减喷头，增Mulch区滴灌 | 承包商 |
| 排水管改道 | 落水管地面暴露 | Patio前地下埋管改道 | 承包商 |
| South Pathway | 现有水泥，保留 | 两侧补种耐旱植物 | DIY |

# 二、施工前准备

- ⚠️ 拨打 811（Colorado法定）：标记所有地下管线，施工前至少3个工作日，免费。

- 标记现有灌溉管道：在扩展Patio区域全面标记两条主管和8个喷头位置。

- 确认退线：东侧退线15ft，北侧和南侧退线各5ft。

- HOA审批：Sterling Ranch HOA，大型改造需提前4-6周申请。

- 拍照记录现状：施工前全面拍照存档。

## 工具与材料清单（含用量估算）

| 工具/材料 | 用途 | 规格/用量 | 费用估算 | 备注 |
| --- | --- | --- | --- | --- |
| 振动夯（租） | 基层压实 | 1-2天 | $80-120/天 | Home Depot可租 |
| 切割机/角磨机（租） | 石板切割 | 1-2天 | $30-60/天 | 弧形切角必用 |
| 水平仪（4ft） | 找平 | 1把 | $30-60（购） | 必备 |
| 铲草机（租） | 去除草皮 | 1天 | $60-80/天 | 612 sqft草皮 |
| 手推车、铁锹 | 搬运 | — | $50-100（租/购） |  |
| 橡皮锤 | 石板就位 | 1把 | $15-25 |  |
| Class 6碎石基层 | Patio基础，4英寸厚 | ~5 cu yd（约135 cu ft） | $200-350 | 360 sqft×4"，含5%损耗 |
| 粗砂找平层 | Patio找平，1英寸厚 | ~1.5 cu yd（约34 cu ft） | $50-100 | 360 sqft×1"，含5%损耗 |
| 天然石板（Flagstone） | Patio铺装 | ~396 sqft（约3-4吨） | $1,200-2,400 | 360 sqft+10%切割损耗 |
| 混凝土大板24"×24" | Patio铺装（替代石板） | ~100块（396 sqft） | $600-1,200 | 每块4 sqft，约1,800 lb |
| 座椅矮墙砌块（8×8×16"） | 座椅矮墙 | ~33块（14ft长×3层） | $80-150 | 或用天然石 |
| 砂浆（Mortar Mix） | 座椅矮墙砌筑 | ~2袋（60 lb/袋） | $20-40 |  |
| 多态砂（Polymeric Sand） | Patio缝隙填充 | ~4袋（50 lb/袋） | $60-100 | 360 sqft约需3-4袋 |
| 金属收边条（Flexible） | 铺装边界固定 | ~60 ft | $50-100 | 含弧形切角段 |
| PVC套管（4英寸） | 灌溉管穿越Patio | ~30 ft | $20-40 | 承包商施工 |
| 弹性填缝剂 | 伸缩缝处理 | ~2支（10 oz/支） | $15-25 | 东扩与楼梯/Pathway接缝 |
| 商业级Weed Barrier | Mulch种植区 | ~675 sqft（含10%损耗） | $50-100 | 612 sqft×1.1 |
| 黑色染色Mulch | Mulch区覆盖3英寸 | ~6 cu yd（约162 cu ft） | $180-300 | 612 sqft×3"，含损耗 |
| Garden Box周边Mulch | 通道覆盖2英寸 | ~1 cu yd（约16 cu ft） | $30-60 | ~96 sqft×2" |
| 脚踏石板（24×18"） | Mulch区小路 | ~10块（约33 sqft） | $80-160 | 间距约2ft |
| Fine Fescue草种 | 草坪补种 | ~5 lb（覆盖870 sqft） | $50-100 | 建议播种率：5-6 lb/1000 sqft |
| 优质Topsoil | 草坪改良，2-3英寸 | ~5 cu yd（约145 cu ft） | $100-200 | 870 sqft×2.5"平均 |
| 秸秆（Straw） | 草种覆盖保湿 | ~2 bales | $20-40 | 约870 sqft |
| U形钉（Garden Staples） | 固定Weed Barrier | ~100个 | $10-20 | 每平方约0.15个 |

# 三、Phase 0 — 灌溉改道 & 排水管处理（承包商）

此阶段必须在Phase 1铺装开始之前完成。

## 灌溉系统改造

现有配置

- 西侧主管：楼梯东侧附近，南北走向，4个喷头，从北侧扩展区引入。

- 东侧主管：草坪东边附近，南北走向，4个喷头，从北侧扩展区引入。

- 两条主管均从北侧扩展Patio区域下方穿过。

改造内容与数量

- PVC套管预埋：4英寸PVC套管，长度约30ft（覆盖两条管道穿越Patio区域），两端各伸出Patio边缘12英寸。

- 西管改道：向东平移约4ft，新埋管长度约28ft（覆盖草坪段南北走向）。

- 喷头调整：每管4个→3个，封堵2个喷头，安装2个180度半圆喷嘴（覆盖半径约12ft）。

- Mulch区滴灌：从西侧主管接出支管，滴灌管铺设约612 sqft（Mulch种植区全覆盖），间距12英寸。

| 工序 | 数量/规格 | 难度 | 费用估算 |
| --- | --- | --- | --- |
| PVC套管预埋 | 4"×30ft | ★★☆☆☆ | $100-200 |
| 西管东移改道 | 约4ft平移，28ft新管 | ★★☆☆☆ | $150-250 |
| 喷头调整（8→6） | 封堵2个，换嘴2个 | ★☆☆☆☆ | $100-150 |
| Mulch区滴灌新增 | 612 sqft，间距12" | ★★☆☆☆ | $200-350 |
| 合计 |  | 承包商 | $800-1,200 |

## 排水落水管改道

- 现状：落水管出口在北侧扩展Patio范围内，需在铺装前改道。

- 方案：4英寸PVC地下埋管，长度约12ft，埋深12英寸，引至Patio边缘草坪侧，安装pop-up emitter排水口。

- 费用：约$200-400，可与灌溉承包商一并完成。

# 四、Phase 1 — Patio区域施工（DIY为主）

建议施工季节：5-9月，避免秋末冻融期。

## 1.1 场地清理

- 清理现有Patio杂物。

- 北侧扩展区（14ft×15ft=210 sqft）：去除草皮和碎石，挖深6英寸 → 挖方约105 cu ft（~3.9 cu yd）。

- 东扩通道（4ft×20ft=80 sqft）：去除草皮，挖深6英寸 → 挖方约40 cu ft（~1.5 cu yd）。

- 东扩南部水泥条（4ft×18ft=72 sqft）：去除草皮，挖深6英寸 → 挖方约36 cu ft（~1.3 cu yd）。

- 三区合计挖方：约181 cu ft（~6.7 cu yd），需租小型翻斗车或多次手推车运出。

## 1.2 基层施工

| 区域 | 面积 | 碎石4"用量 | 砂1"用量 | 备注 |
| --- | --- | --- | --- | --- |
| 北侧扩展Patio | 210 sqft | 70 cu ft / 2.6 cu yd | 17.5 cu ft / 0.65 cu yd | 坡度10%，注意找平 |
| 东扩通道 | ~78 sqft | 26 cu ft / 0.96 cu yd | 6.5 cu ft / 0.24 cu yd | 含弧形切角区 |
| 东扩南部水泥条 | 72 sqft | 24 cu ft / 0.89 cu yd | 6 cu ft / 0.22 cu yd | 坡度13%，排水向南 |
| 合计（+5%损耗） | ~360 sqft | ~126 cu ft / ~5 cu yd | ~32 cu ft / ~1.5 cu yd |  |

- 夯实原土层：振动夯2-3遍。

- 铺碎石基层：每2英寸一层，每层夯实后再铺下一层，共2层达4英寸。

- 坡度控制：铺装面整体保持2%排水坡，引导雨水向草坪侧排出。

- 台地处理：北扩Patio比现有Patio低约12-15英寸，座椅矮墙处为分界线。

- 铺1英寸粗砂找平层，刮平板整平，不夯实。

## 1.3 北侧扩展Patio铺装（210 sqft）

| 材料选项 | 用量 | 重量/数量 | 材料费 | 备注 |
| --- | --- | --- | --- | --- |
| 天然石板（Flagstone） | 231 sqft（+10%损耗） | 约3,500-4,600 lb（1.75-2.3吨） | $900-1,850 | 厚1.5-2"，约15-20 lb/sqft |
| 混凝土大板（24"×24"） | 58块（+10%损耗） | 约1,044 lb（~0.5吨） | $580-870 | 每块4 sqft，约18 lb/块 |

- 从座椅矮墙处向北铺设，保证与现有Patio齐平过渡。

- 石板间距0.5-1英寸，完工后填充多态砂（约2袋/100 sqft，共需约4.5袋）。

- 座椅矮墙（14ft长）：混凝土砌块约33块（3层×11块），砂浆约2袋（60 lb/袋）。

## 1.4 东扩通道施工（~78 sqft）

范围与尺寸

- 东扩通道：楼梯东侧，宽4ft，从房屋北墙线向南至楼梯底部，约20ft长，去除弧形缺口后约78 sqft。

- 东扩南部水泥条：同宽4ft，从楼梯底部向南至South Pathway，约18ft长，约72 sqft。

- 两段合计：约150 sqft，铺装用量约165 sqft（+10%损耗）。

弧形切角施工

- 切角范围：从现有Patio东北角（X=192,Y=225）弧切至东扩通道（X=224,Y=257），弧线长约45英寸，切除三角约0.5 sqft。

- 放样：粉笔在砂层画弧线，确认后切割。

- 切割：角磨机分3-4刀沿弧线切割，每刀入深约1/3，最后贯通，避免崩裂。

- 弧形收边：安装flexible metal edging，沿弧线弯曲固定，每隔12英寸打入固定钉。

关键衔接处理

- 楼梯东侧缝：东扩通道与楼梯水泥面之间留0.5英寸伸缩缝，填充弹性填缝剂（约半支，5 oz）。

- South Pathway接缝：东扩南端与South Pathway之间同样留0.5英寸伸缩缝（约1支，10 oz）。

- 高度对齐：东扩通道顶面与楼梯面齐平或低0.25英寸，13%坡段确保排水方向向南。

## 1.5 Fire Pit区找平

- 圆形区域直径10ft，面积约79 sqft。

- 挖低6-8英寸（挖方约37-49 cu ft，约1.4-1.8 cu yd）。

- 铺碎石基层4英寸：约26 cu ft（~1 cu yd）。

- 外围圆形金属收边条或石材围边，周长约31ft。

# 五、Phase 2 — 草坪改造 & Mulch种植区（DIY）

建议施工季节：早春（3-4月）或初秋（8-9月）。

## 2.1 草坪改造

| 项目 | 数据 | 备注 |
| --- | --- | --- |
| 草坪保留面积 | ~870 sqft（约34ft×28ft，减去Fire Pit圆形79 sqft） | 集中在北侧遮荫较好区域 |
| 需移除草皮面积 | ~612 sqft（约34ft×18ft，南侧改Mulch区） | 用铲草机去除 |
| Topsoil补充量 | ~5 cu yd（870 sqft×2.5"平均厚度） | 约145 cu ft |
| 草种用量 | ~5 lb（870 sqft，播种率5-6 lb/1000 sqft） | Fine Fescue 或 Tall Fescue |
| 秸秆覆盖 | ~2 bales（约870 sqft，1 bale覆盖约500 sqft） | 保湿防鸟 |
| 金属收边条 | 约56ft（草坪东/南/西边界总长） | 含弯角处理 |

- Step 1：安装金属收边条，标记新草坪边界。

- Step 2：铲草机去除南侧612 sqft草皮（建议租铲草机，手工挖耗时约2倍）。

- Step 3：保留区补土5 cu yd，深翻8英寸（约870 sqft区域）。

- Step 4：沿东侧围栏内侧铺weed barrier约2ft宽×66ft长≈132 sqft，上覆mulch约3英寸（约22 cu ft，约0.8 cu yd）。

- Step 5：播种，覆秸秆，持续浇水至发芽（通常7-14天）。

## 2.2 Mulch种植区（612 sqft）

| 材料 | 用量计算 | 用量结果 | 费用估算 |
| --- | --- | --- | --- |
| 商业级Weed Barrier | 612 sqft × 1.1（损耗） | ~675 sqft | $50-100 |
| U形固定钉 | 675 sqft × 0.15个/sqft | ~100个 | $10-20 |
| 黑色染色Mulch（3英寸厚） | 612 sqft × 3" / 12 × 1.1（损耗） | ~168 cu ft / ~6.2 cu yd | $185-310 |
| 脚踏石板（24×18"） | 10块，每块3 sqft，共30 sqft | 约33 sqft（+10%） | $80-160 |
| 脚踏石板下垫砂 | 每块0.1 cu ft砂 | 约1 cu ft | 含砂层费用 |

- Step 1：清除区域碎石和草皮，挖深约4英寸（612 sqft × 4" = 204 cu ft ≈ 7.6 cu yd）。

- Step 2：整平，铺商业级Weed Barrier，U形钉每3ft固定。

- Step 3：脚踏石板布局：在景观布上摆放确认，剪孔，每块下垫砂约0.1 cu ft找平，石板顶面高出mulch约0.5英寸。

- Step 4：覆盖黑色Mulch约6.2 cu yd（约168 cu ft），厚度均匀保持3英寸。

## 2.3 Garden Box区域整理

- 现有3个Box保留。

- 周边通道mulch：3个Box×2面×(8ft×2ft)=96 sqft，覆mulch 2英寸≈16 cu ft≈0.6 cu yd，约$20-40。

- 梨树围树mulch：直径3ft圆形≈7 sqft，覆mulch 3英寸≈1.75 cu ft，含在上述用量内。

# 六、施工时间线

| 阶段 | 内容 | 时长 | 季节 | 方式 |
| --- | --- | --- | --- | --- |
| Phase 0-A | 灌溉系统改造（套管+改道+喷头+滴灌） | 1-2天 | 施工季前 | 承包商 |
| Phase 0-B | 排水落水管改道（PVC埋管12ft） | 半天 | 施工季前 | 承包商 |
| Phase 1-A | 场地清理（三区合计挖方~6.7 cu yd） | 1天 | 5-9月 | DIY |
| Phase 1-B | 基层施工（碎石5 cu yd+砂1.5 cu yd夯实） | 1天 | 5-9月 | DIY |
| Phase 1-C | 北扩Patio铺装（210 sqft）+座椅矮墙（14ft） | 2-3天 | 5-9月 | DIY/半DIY |
| Phase 1-D | 东扩通道（78 sqft）+弧形切角+衔接处理 | 1-2天 | 5-9月 | DIY |
| Phase 1-E | 东扩南部水泥条（72 sqft）+Pathway接缝 | 1天 | 5-9月 | DIY |
| Phase 1-F | Fire Pit找平（79 sqft圆形，挖方~1.6 cu yd） | 半天 | 5-9月 | DIY |
| Phase 2-A | 草坪改造（移除612 sqft+补种870 sqft） | 1-2天 | 3-4月/8-9月 | DIY |
| Phase 2-B | Mulch种植区（612 sqft，6.2 cu yd mulch） | 1-2天 | 春/秋 | DIY |
| Phase 2-C | Garden Box周边整理（96 sqft） | 半天 | 随时 | DIY |

总DIY工时估算：约10-14个工作日

# 七、预算估算

| 类别 | 项目 | 规格/用量 | 低估 | 高估 |
| --- | --- | --- | --- | --- |
| 承包商 | 灌溉改造（套管30ft+改道+喷头+滴灌612 sqft） |  | $800 | $1,200 |
| 承包商 | 排水管改道（4"PVC，12ft埋管） |  | $200 | $400 |
| Phase 1 | 碎石基层（Class 6） | ~5 cu yd | $200 | $350 |
| Phase 1 | 粗砂找平层 | ~1.5 cu yd | $50 | $100 |
| Phase 1 | 天然石板（Flagstone） | ~396 sqft / 3-4吨 | $1,200 | $2,400 |
| Phase 1 | （替代）混凝土大板24"×24" | ~100块 / ~1,800 lb | $600 | $1,200 |
| Phase 1 | 座椅矮墙砌块（8×8×16"）+砂浆 | 33块+2袋 | $100 | $190 |
| Phase 1 | 多态砂 | ~4袋（50 lb/袋） | $60 | $100 |
| Phase 1 | 金属收边条（含flexible弧形段） | ~60 ft | $50 | $100 |
| Phase 1 | 弹性填缝剂 | ~1.5支（10 oz/支） | $15 | $25 |
| Phase 1 | 工具租赁（夯机2天+切割机1天+铲草机1天） |  | $230 | $380 |
| Phase 2 | Topsoil草坪改良 | ~5 cu yd | $100 | $200 |
| Phase 2 | Fine Fescue / Tall Fescue草种 | ~5 lb | $50 | $100 |
| Phase 2 | 秸秆（Straw） | ~2 bales | $20 | $40 |
| Phase 2 | 商业级Weed Barrier | ~675 sqft | $50 | $100 |
| Phase 2 | 黑色染色Mulch（Mulch区6.2 cu yd+围树0.8 cu yd） | ~7 cu yd | $210 | $350 |
| Phase 2 | 脚踏石板（24×18"） | ~10块 | $80 | $160 |
| Phase 2 | U形钉 | ~100个 | $10 | $20 |
| 其他 | 杂项（粉笔线、手套、刷子等） |  | $50 | $100 |
| DIY合计（石板方案） |  |  | $2,325 | $4,725 |
| DIY合计（混凝土板方案） |  |  | $1,725 | $4,025 |
| 总计含承包商（石板方案） |  |  | $3,325 | $6,325 |
| 总计含承包商（混凝土板方案） |  |  | $2,725 | $5,625 |

# 八、Colorado / Douglas County 特别注意事项

## 气候

- 冻融循环：基层必须4英寸压实碎石，否则铺装1-2年内开裂。

- 干旱：年降水约15英寸，草种和植物选择优先USDA Zone 5b-6a耐旱品种。

- 大风：Fire Pit使用注意风向，围栏外开阔草地风速高。

- 冰雹：5-8月冰雹季，石材/混凝土铺装比木材更耐用。

## 法规

- ⚠️ 811管线定位：Colorado法律强制要求，违规损坏管线须承担全部维修费用。

- HOA审批：Sterling Ranch HOA，大型改造建议提前查阅CC&Rs或联系HOA。

- 退线：东侧15ft，北/南侧各5ft，永久构筑物须符合退线要求。

- 灌溉节水：建议安装智能控制器（rain sensor），部分水公司有补贴。

# 九、DIY难点提示

| 施工环节 | 难度 | 最大挑战 | 建议 |
| --- | --- | --- | --- |
| Patio基层夯实 | ★★☆☆☆ | 坡度均匀、排水方向 | 租振动夯，每点检查2%排水坡 |
| 天然石板铺装 | ★★★☆☆ | 不规则拼接和切割 | 先干铺全排，满意后再固定 |
| 座椅矮墙砌筑 | ★★★☆☆ | 找平和稳固 | 砂浆砌筑，每3层检查水平 |
| 弧形切角切割 | ★★★☆☆ | 曲线精度，石板不崩裂 | 粉笔放样，角磨机分多刀切割 |
| 东扩与楼梯衔接 | ★★☆☆☆ | 高度对齐，伸缩缝处理 | 提前测量楼梯面高度，留0.5"缝 |
| 13%坡铺装 | ★★★☆☆ | 坡面不滑动，排水向南 | 选粗糙面石板，基层夯实更关键 |
| 草坪补种（干旱） | ★★☆☆☆ | 种子发芽率低 | 秸秆覆盖保湿，每天浇水7-14天 |

— 中文部分完 —

Backyard Renovation Construction Plan

8958 Fraser River Street, Littleton, CO

Lot 137 · Sterling Ranch Filing No. 4A · Douglas County

Elevation 5,721 ft · Lot Area 6,448 sq ft

# I. Project Overview

This plan is based on the Plot Plan (Aztec Consultants, dated 5/18/2021) and on-site photographs. The renovation aims to transform an underutilized backyard into a fully functional outdoor living space, reduce lawn maintenance burden, and preserve play area for children and pets.

## Key Property Data

| Item | Value | Notes |
| --- | --- | --- |
| Backyard Width (N-S) | 66.19 ft | East fence span |
| Backyard Depth (E-W) | ~45 ft | House rear wall to east fence |
| North Side Setback | 18.1 ft | House north wall to north fence |
| South Side (Pathway) | 9.96 ft | Existing concrete path |
| Deck / Patio | 20 × 10 ft | Within house footprint |
| Staircase | 20 ft × ~4 ft | Cantilevered on east wall |
| Rear Yard Setback | 15 ft | Douglas County requirement |
| Lawn Slope | 7.9% | Slopes east |
| South Pathway Slope | 13% | Existing concrete, retained |
| North Extension Area Slope | 10% | Expanded patio zone |

## Renovation Scope Summary

| Zone | Current State | Renovation | Method |
| --- | --- | --- | --- |
| North Patio Extension | Gravel + lawn | New flagstone/concrete paver patio, dining + grill area, seat wall | DIY / Semi-DIY |
| East Corridor | Lawn | 4 ft wide paver path east of staircase, curved cut connecting north patio | DIY |
| East South Concrete Strip | Lawn | 4 ft wide, extends to South Pathway, completing circulation loop | DIY |
| Existing Patio Renovation | Concrete (cluttered) | Clear and tidy, primary activity area | DIY |
| Fire Pit Zone | Lawn/gravel | Level pad, portable fire pit | DIY |
| Lawn Renovation | Sparse, weed-prone | Reduce to ~870 sqft, reseed drought-tolerant grass | DIY |
| Mulch Planting Bed | Gravel | Weed barrier + mulch + stepping stones | DIY |
| East Buffer Strip | Gravel + black mulch (existing) | Retain as-is | No work needed |
| Garden Boxes (×3) | 3 existing boxes | Retain, tidy mulch pathways around boxes | DIY minor |
| Irrigation System | 2 pipes, 8 heads | Reroute pipes, reduce heads, add drip irrigation | Contractor |
| Downspout Reroute | Surface exposed | Underground PVC reroute before patio work | Contractor |
| South Pathway | Existing concrete, retained | Plant drought-tolerant plants on both sides | DIY |

# II. Pre-Construction Checklist

- ⚠️ Call 811 (Colorado law): Locate all underground utilities at least 3 business days before digging. Free service.

- Mark existing irrigation lines: Flag both main pipes and all 8 sprinkler heads in the patio extension zone.

- Verify setbacks: East rear setback 15 ft, north and south side setbacks 5 ft each.

- HOA approval: Sterling Ranch HOA — submit application 4-6 weeks before construction for any major hardscaping or planting.

- Photo document existing conditions before any work begins.

## Tools & Materials with Quantity Estimates

| Tool / Material | Purpose | Qty / Spec | Est. Cost | Notes |
| --- | --- | --- | --- | --- |
| Plate Compactor (rental) | Base compaction | 1-2 days | $80-120/day | Available at Home Depot |
| Angle Grinder / Tile Saw (rental) | Stone cutting | 1-2 days | $30-60/day | Required for curved cut |
| 4 ft Level | Grade checking | 1 unit | $30-60 (purchase) | Essential |
| Sod Cutter (rental) | Remove existing lawn | 1 day | $60-80/day | Removes 612 sqft of sod |
| Wheelbarrow, Shovels | Material handling | — | $50-100 |  |
| Rubber Mallet | Setting pavers | 1 unit | $15-25 |  |
| Class 6 Aggregate Base | 4" patio base | ~5 cu yd (~135 cu ft) | $200-350 | 360 sqft × 4", incl. 5% waste |
| Coarse Sand (bedding layer) | 1" leveling layer | ~1.5 cu yd (~34 cu ft) | $50-100 | 360 sqft × 1", incl. 5% waste |
| Natural Flagstone | Patio paving | ~396 sqft (~3,500-4,600 lb) | $1,200-2,400 | 1.5-2" thick, 15-20 lb/sqft |
| Concrete Pavers 24"×24" | Alt. patio paving | ~100 units (~1,800 lb) | $600-1,200 | 4 sqft/unit, ~18 lb/unit |
| CMU Blocks 8×8×16" | Seat wall | ~33 units (14 ft × 3 courses) | $80-150 | Or natural stone |
| Mortar Mix (60 lb bags) | Seat wall | ~2 bags | $20-40 |  |
| Polymeric Sand (50 lb bags) | Paver joint fill | ~4 bags (~200 lb) | $60-100 | ~1 bag per 100 sqft |
| Flexible Metal Edging | Paver restraint | ~60 ft | $50-100 | Curved for arc cut section |
| 4" PVC Conduit (sleeve) | Irrigation sleeve under patio | ~30 ft | $20-40 | Contractor installs |
| Flexible Polyurethane Sealant | Expansion joints | ~1.5 tubes (10 oz) | $15-25 | At staircase + pathway joints |
| Commercial Weed Barrier | Mulch bed base | ~675 sqft (incl. 10% waste) | $50-100 | 612 sqft × 1.1 |
| Garden Staples / U-pins | Secure weed barrier | ~100 units | $10-20 |  |
| Black Dyed Mulch | 3" cover over planting bed | ~6.2 cu yd (~168 cu ft) | $185-310 | 612 sqft × 3" |
| Mulch for Garden Box paths | 2" cover, box surrounds | ~0.6 cu yd (~16 cu ft) | $30-60 | ~96 sqft × 2" |
| Stepping Stones 24×18" | Path through mulch bed | ~10 units (~33 sqft) | $80-160 | Set 0.5" above mulch |
| Fine Fescue / Tall Fescue Seed | Lawn reseeding | ~5 lb (870 sqft) | $50-100 | Seeding rate ~5-6 lb/1,000 sqft |
| Premium Topsoil | 2.5" lawn amendment | ~5 cu yd (~145 cu ft) | $100-200 | 870 sqft × 2.5" avg |
| Straw Mulch | Seed cover/moisture retention | ~2 bales | $20-40 | ~1 bale / 500 sqft |

# III. Phase 0 — Irrigation Reroute & Downspout (Contractor)

Must be completed before any Phase 1 paving work begins.

## Irrigation System Renovation

Existing Configuration

- West main pipe: near east side of staircase, N-S orientation, 4 sprinkler heads, enters from north extension zone.

- East main pipe: near east edge of lawn, N-S orientation, 4 sprinkler heads, enters from north extension zone.

- Both pipes run under the proposed north patio extension area.

Renovation Scope & Quantities

- PVC conduit sleeves: 4" PVC, ~30 ft total, extending 12" beyond patio edge on both ends — protects pipes and allows future maintenance without breaking pavers.

- West pipe reroute: shift ~4 ft east to clear east corridor pavers; new burial ~28 ft N-S.

- Head reduction: 8 heads → 6 heads; cap 2 heads, install 2 × 180° half-circle nozzles (radius ~12 ft) facing inward toward lawn.

- Drip irrigation for mulch bed: branch from west main pipe, ~612 sqft coverage, drip line spacing 12".

| Task | Qty / Spec | Difficulty | Est. Cost |
| --- | --- | --- | --- |
| PVC conduit sleeve installation | 4" × 30 ft | ★★☆☆☆ | $100-200 |
| West pipe reroute | ~4 ft shift, 28 ft new pipe | ★★☆☆☆ | $150-250 |
| Sprinkler head adjustment (8→6) | Cap 2, replace nozzles 2 | ★☆☆☆☆ | $100-150 |
| Mulch bed drip line installation | 612 sqft, 12" spacing | ★★☆☆☆ | $200-350 |
| Total |  | Contractor | $800-1,200 |

## Downspout Reroute

- Issue: Downspout outlet falls within proposed north patio extension — must be rerouted before paving.

- Solution: 4" PVC underground pipe, ~12 ft length, buried ~12" deep, routed to lawn edge with pop-up emitter outlet.

- Cost: ~$200-400, can be combined with irrigation contractor visit.

- ⚠️ Timing: Complete before patio base course installation.

# IV. Phase 1 — Patio Construction (Primarily DIY)

Recommended season: May – September. Avoid late fall — Colorado freeze-thaw cycles will damage incompletely cured base.

## 1.1 Site Clearing

- Clear all items from existing walkout patio area.

- North patio extension (14 ft × 15 ft = 210 sqft): Remove sod and gravel, excavate 6" deep → ~105 cu ft (~3.9 cu yd) of spoil.

- East corridor (4 ft × 20 ft = 80 sqft): Remove sod, excavate 6" → ~40 cu ft (~1.5 cu yd) of spoil.

- East south concrete strip (4 ft × 18 ft = 72 sqft): Remove sod, excavate 6" → ~36 cu ft (~1.3 cu yd) of spoil.

- Total excavation: ~181 cu ft (~6.7 cu yd). Rent a mini-dumper or use multiple wheelbarrow loads to haul out.

## 1.2 Base Course Installation

| Zone | Area | 4" Aggregate Base | 1" Sand Bedding | Notes |
| --- | --- | --- | --- | --- |
| North Patio Extension | 210 sqft | 70 cu ft / 2.6 cu yd | 17.5 cu ft / 0.65 cu yd | 10% slope — careful grading |
| East Corridor | ~78 sqft | 26 cu ft / 0.96 cu yd | 6.5 cu ft / 0.24 cu yd | Includes curved cut zone |
| East South Strip | 72 sqft | 24 cu ft / 0.89 cu yd | 6 cu ft / 0.22 cu yd | 13% slope — drain south |
| Total (+ 5% waste) | ~360 sqft | ~126 cu ft / ~5 cu yd | ~32 cu ft / ~1.5 cu yd |  |

- Compact subgrade with plate compactor, 2-3 passes.

- Install aggregate base in 2" lifts, compacting each lift before adding the next — total 4" compacted depth.

- Maintain 2% drainage slope across all paved surfaces, directing water away from the house toward the lawn.

- Terrace transition: North extension sits ~12-15" lower than existing patio — seat wall marks the level change.

- Spread 1" sand bedding layer, screed flat; do not compact.

## 1.3 North Patio Extension Paving (210 sqft)

| Material Option | Quantity | Weight | Material Cost | Notes |
| --- | --- | --- | --- | --- |
| Natural Flagstone | 231 sqft (+10% waste) | ~3,500-4,600 lb (1.75-2.3 tons) | $1,200-2,400 | 1.5-2" thick, 15-20 lb/sqft |
| Concrete Pavers 24"×24" | 58 units (+10% waste) | ~1,044 lb (~0.5 tons) | $580-870 | 4 sqft/unit, ~18 lb/unit |

- Begin at seat wall and work north, ensuring flush transition with existing patio.

- Maintain 0.5-1" joints between pavers; fill with polymeric sand after full installation (~4 bags total).

- Seat wall (14 ft long): ~33 CMU blocks (3 courses × ~11 blocks per course), set in mortar (~2 bags mortar mix).

## 1.4 East Corridor Construction (~78 sqft)

Scope & Dimensions

- East corridor: 4 ft wide, east of staircase, from house north wall line south to staircase base — ~20 ft long, ~78 sqft net (after curved cut).

- East south strip: same 4 ft width, from staircase base south to South Pathway — ~18 ft long, ~72 sqft.

- Combined: ~150 sqft; order ~165 sqft of paving material (+10% cutting waste).

Curved Cut Installation (Key Challenge)

- Cut location: From existing patio NE corner (192,225) arcing to east corridor (224,257), 45° direction; arc length ~45", removed triangle area ~0.5 sqft.

- Layout: Mark arc with chalk on sand bed before cutting.

- Cutting: Use angle grinder in 3-4 passes along arc — each pass ~1/3 depth to avoid blow-out; final pass breaks through cleanly.

- Edge restraint: Install flexible metal edging along arc; stake every 12".

Critical Joints

- East corridor / staircase joint: Leave 0.5" expansion gap; fill with flexible polyurethane sealant (~5 oz / half tube).

- East south strip / South Pathway joint: Leave 0.5" expansion gap; fill with sealant (~10 oz / 1 tube).

- Height alignment: East corridor surface flush with or 0.25" below staircase surface — no trip hazard.

## 1.5 Fire Pit Zone

- 10 ft diameter circle, area ~79 sqft.

- Excavate 6-8" deep → ~37-49 cu ft (~1.4-1.8 cu yd) of spoil.

- Install 4" compacted aggregate base → ~26 cu ft (~1 cu yd).

- Install circular metal edging or stone border (~31 ft perimeter).

# V. Phase 2 — Lawn & Mulch Bed (DIY)

Best season: Early spring (March-April) or early fall (August-September) for seed germination.

## 2.1 Lawn Renovation

| Item | Data | Notes |
| --- | --- | --- |
| Lawn retention area | ~870 sqft (~34 ft × 28 ft, minus 79 sqft fire pit circle) | Focus on north zone — better shade, better existing turf |
| Sod removal area | ~612 sqft (~34 ft × 18 ft, south section to become mulch bed) | Use sod cutter rental |
| Topsoil amendment | ~5 cu yd (~145 cu ft) — 870 sqft × 2.5" avg. depth | Spread and till 8" deep |
| Grass seed quantity | ~5 lb (870 sqft at 5-6 lb/1,000 sqft seeding rate) | Fine Fescue or Tall Fescue |
| Straw mulch cover | ~2 bales (~870 sqft, 1 bale ≈ 500 sqft) | Retain moisture, deter birds |
| Metal edging | ~56 ft (east + south + west lawn perimeter) | Include corner bends |

- Step 1: Install metal edging to define new lawn perimeter.

- Step 2: Rent sod cutter to remove 612 sqft of sod from south section.

- Step 3: Amend retained 870 sqft area: spread ~5 cu yd topsoil, till 8" deep.

- Step 4: Install weed barrier along east fence interior: ~2 ft wide × 66 ft long = ~132 sqft; cover with 3" mulch (~22 cu ft / ~0.8 cu yd).

- Step 5: Broadcast seed, cover with straw, water daily until germination (typically 7-14 days).

## 2.2 Mulch Planting Bed (612 sqft)

| Material | Calculation | Quantity | Est. Cost |
| --- | --- | --- | --- |
| Commercial Weed Barrier | 612 sqft × 1.1 waste factor | ~675 sqft | $50-100 |
| Garden Staples / U-pins | 675 sqft × 0.15 pins/sqft | ~100 units | $10-20 |
| Black Dyed Mulch (3" depth) | 612 sqft × 3" / 12 × 1.1 | ~168 cu ft / ~6.2 cu yd | $185-310 |
| Stepping Stones 24×18" | 10 units × 3 sqft = 30 sqft | ~33 sqft (+10%) | $80-160 |
| Sand under stepping stones | 10 units × ~0.1 cu ft each | ~1 cu ft | Incl. in sand budget |

- Step 1: Remove existing gravel and sod — excavate ~4" deep; ~204 cu ft (~7.6 cu yd) of material to remove.

- Step 2: Grade and level; install commercial weed barrier; staple every 3 ft.

- Step 3: Lay stepping stones — mark positions, cut barrier, bed each stone on ~0.1 cu ft of sand; set 0.5" proud of final mulch surface.

- Step 4: Spread ~6.2 cu yd of black dyed mulch evenly at 3" depth.

## 2.3 Garden Box Area Tidying

- All 3 existing garden boxes retained — no structural work needed.

- Mulch pathways around boxes: 3 boxes × 2 sides × (8 ft × 2 ft) = 96 sqft; cover with 2" mulch → ~16 cu ft (~0.6 cu yd), est. $20-40.

- Pear tree mulch ring: ~3 ft diameter circle (~7 sqft), 3" depth, ~1.75 cu ft; keep 6" clear of trunk.

# VI. Construction Schedule

| Phase | Scope | Duration | Season | Method |
| --- | --- | --- | --- | --- |
| Phase 0-A | Irrigation reroute (sleeve 30 ft + west pipe + heads + drip 612 sqft) | 1-2 days | Pre-season | Contractor |
| Phase 0-B | Downspout reroute (4" PVC, 12 ft burial) | Half day | Pre-season | Contractor |
| Phase 1-A | Site clearing (excavate ~6.7 cu yd across 3 zones) | 1 day | May-Sep | DIY |
| Phase 1-B | Base course (5 cu yd aggregate + 1.5 cu yd sand, compact) | 1 day | May-Sep | DIY |
| Phase 1-C | North patio paving (210 sqft) + seat wall (14 ft) | 2-3 days | May-Sep | DIY/Semi-DIY |
| Phase 1-D | East corridor (78 sqft) + curved cut + joints | 1-2 days | May-Sep | DIY |
| Phase 1-E | East south strip (72 sqft) + Pathway joint | 1 day | May-Sep | DIY |
| Phase 1-F | Fire pit zone (79 sqft circle, excavate ~1.6 cu yd) | Half day | May-Sep | DIY |
| Phase 2-A | Lawn reno (remove 612 sqft + reseed 870 sqft) | 1-2 days | Mar-Apr / Aug-Sep | DIY |
| Phase 2-B | Mulch bed (612 sqft, 6.2 cu yd mulch) | 1-2 days | Spring/Fall | DIY |
| Phase 2-C | Garden box area tidying (96 sqft mulch paths) | Half day | Anytime | DIY |

Total estimated DIY labor: 10-14 working days (splittable across weekends)

# VII. Budget Estimate

| Category | Item | Qty / Spec | Low Est. | High Est. |
| --- | --- | --- | --- | --- |
| Contractor | Irrigation reroute (sleeve + pipe + heads + drip 612 sqft) |  | $800 | $1,200 |
| Contractor | Downspout reroute (4" PVC, 12 ft) |  | $200 | $400 |
| Phase 1 | Class 6 aggregate base | ~5 cu yd | $200 | $350 |
| Phase 1 | Coarse sand bedding | ~1.5 cu yd | $50 | $100 |
| Phase 1 | Natural flagstone | ~396 sqft / 3-4 tons | $1,200 | $2,400 |
| Phase 1 | (Alt.) Concrete pavers 24"×24" | ~100 units / ~1,800 lb | $600 | $1,200 |
| Phase 1 | CMU seat wall blocks + mortar | 33 units + 2 bags | $100 | $190 |
| Phase 1 | Polymeric sand | ~4 bags (50 lb ea.) | $60 | $100 |
| Phase 1 | Metal edging (incl. flexible section) | ~60 ft | $50 | $100 |
| Phase 1 | Flexible polyurethane sealant | ~1.5 tubes (10 oz ea.) | $15 | $25 |
| Phase 1 | Tool rentals (compactor 2d + grinder 1d + sod cutter 1d) |  | $230 | $380 |
| Phase 2 | Premium topsoil | ~5 cu yd | $100 | $200 |
| Phase 2 | Fine/Tall Fescue seed | ~5 lb | $50 | $100 |
| Phase 2 | Straw mulch | ~2 bales | $20 | $40 |
| Phase 2 | Commercial weed barrier | ~675 sqft | $50 | $100 |
| Phase 2 | Black dyed mulch (bed 6.2 + paths 0.8 cu yd) | ~7 cu yd | $210 | $350 |
| Phase 2 | Stepping stones 24×18" | ~10 units | $80 | $160 |
| Phase 2 | Garden staples (U-pins) | ~100 units | $10 | $20 |
| Other | Miscellaneous (chalk, gloves, brushes, etc.) |  | $50 | $100 |
| DIY Total (Flagstone option) |  |  | $2,325 | $4,725 |
| DIY Total (Paver option) |  |  | $1,725 | $4,025 |
| Total incl. Contractor (Flagstone) |  |  | $3,325 | $6,325 |
| Total incl. Contractor (Paver) |  |  | $2,725 | $5,625 |

Note: Labor costs for DIY work not included. Semi-DIY option (contractor does base, owner does paving) may save $300-500 on labor but does not reduce material costs.

# VIII. Colorado / Douglas County Notes

## Climate Considerations

- Freeze-thaw cycles: Denver metro ranks among highest in the US. A 4" compacted Class 6 base is non-negotiable — without it, pavers will heave or crack within 1-2 seasons.

- Arid climate: ~15" annual precipitation at this elevation. Prioritize USDA Zone 5b-6a drought-tolerant plant and grass varieties.

- High winds: Sterling Ranch is exposed — open rangeland to the east accelerates wind. Check wind direction before using the fire pit.

- Hail: June-August hail season. Stone and concrete pavers outperform wood decking in hail resistance.

## Regulatory Notes

- ⚠️ Call 811: Colorado state law. Damaging unmarked utilities without calling 811 makes the excavator fully liable for repair costs.

- HOA approval: Review Sterling Ranch CC&Rs and contact HOA before starting any major hardscaping or grading work.

- Setbacks: Rear (east) 15 ft, side (north/south) 5 ft each. All permanent structures must comply.

- Water conservation: Douglas County has timeliness-of-use water rules. A smart irrigation controller with rain sensor can reduce water use 30-50%; some utilities offer rebates.

# IX. DIY Difficulty & Tips

| Task | Difficulty | Key Challenge | Recommendation |
| --- | --- | --- | --- |
| Base course compaction | ★★☆☆☆ | Consistent slope and drainage | Rent plate compactor; check 2% grade at every point |
| Natural flagstone paving | ★★★☆☆ | Irregular fitting and cutting | Dry-lay entire area first; cut only after confirming layout |
| Seat wall construction | ★★★☆☆ | Level and stable courses | Use mortar (not dry-stack); check level every 3 courses |
| Curved cut in paver | ★★★☆☆ | Arc accuracy without chip-out | Chalk layout first; angle grinder in 3-4 shallow passes |
| East corridor / staircase joint | ★★☆☆☆ | Height alignment and joint sealing | Measure stair surface height first; leave 0.5" gap for sealant |
| 13% slope paving | ★★★☆☆ | Paver stability, drainage south | Choose textured face stone; thorough base compaction is critical |
| Lawn reseeding (arid climate) | ★★☆☆☆ | Germination in low humidity | Straw cover + daily watering until green (7-14 days) |

— End of Document —

Based on Plot Plan by Aztec Consultants (5/18/2021) and on-site photographs